## Task_Table
ID | Name | Sub-Task | Duration | Start_Date | Finish_Date | Predecessors | Resource_Names | Notes
1 | HIE Integration |  | 121 days | 2/5/18 8:00 AM | 7/23/18 5:00 PM
2 | Project Set up |  | 10 days | 2/5/18 8:00 AM | 2/16/18 5:00 PM
3 |  | Identify project manager | 1 day | 2/5/18 8:00 AM | 2/5/18 5:00 PM |  | Sponsor
4 |  | Document Project Description | 4 days | 2/6/18 8:00 AM | 2/9/18 5:00 PM | 3 | Project Manager | Include the problem that this project addresses
5 |  | Document Proposed project timeline estimate | 4 days | 2/6/18 8:00 AM | 2/9/18 5:00 PM | 3 | Project Manager | Include key dates and milestones
6 |  | Document Project Value | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM |  | Project Manager
7 |  | Project goals | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM |  |  | Goals are the expected positive outcomes of completing this project
8 |  | Patient care improvements | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM | 5 | Project Manager
9 |  | operational improvements | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM | 5 | Project Manager
10 |  | Quantify project objectives | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM | 5 | Project Manager | Measurable items. # of transactions /month
11 |  | Financial benefits | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM
12 |  | Regulatory mandates | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM | 5 | Project Manager
13 |  | ACO participation requirement | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM | 5 | Project Manager
14 |  | Operational improvements | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM | 5 | Project Manager
15 | Confirm Internal Organization support |  | 15 days | 2/12/18 8:00 AM | 3/2/18 5:00 PM
16 |  | Leadership | 5 days | 2/12/18 8:00 AM | 2/16/18 5:00 PM | 5 | Sponsor | Confirm this project fits with the organizaton's strategic goals and will be supported throughout
17 |  | Direct care staff | 10 days | 2/19/18 8:00 AM | 3/2/18 5:00 PM | 16 | Sponsor | Ensure staff buy in. reduce negativity and apathy
18 |  | IT | 10 days | 2/19/18 8:00 AM | 3/2/18 5:00 PM | 16 | Sponsor | Must be priority
19 |  | Other departments | 10 days | 2/19/18 8:00 AM | 3/2/18 5:00 PM | 16 | Sponsor | Training, HR, Finance
20 |  | Confirm Project Budget | 10 days | 2/19/18 8:00 AM | 3/2/18 5:00 PM | 16
21 |  | IT systems changes or upgrades | 10 days | 2/19/18 8:00 AM | 3/2/18 5:00 PM | 16 | Project Manager
22 |  | Staff and other resources | 10 days | 2/19/18 8:00 AM | 3/2/18 5:00 PM | 16 | Project Manager
23 |  | Organize Staffing | 20 days | 3/5/18 8:00 AM | 3/30/18 5:00 PM
24 |  | Internal | 5 days | 3/5/18 8:00 AM | 3/9/18 5:00 PM
25 |  | Identify Direct care staff representative | 5 days | 3/5/18 8:00 AM | 3/9/18 5:00 PM | 17 | Project Manager
26 |  | IT resource | 5 days | 3/5/18 8:00 AM | 3/9/18 5:00 PM | 18 | Project Manager
27 |  | Other | 5 days | 3/5/18 8:00 AM | 3/9/18 5:00 PM | 18 | Project Manager | Training, HR, Finance
28 |  | External additional resources | 20 days | 3/5/18 8:00 AM | 3/30/18 5:00 PM |  |  | Back fill or support for key staff, IT resources
29 |  | Work estimates and tasks | 10 days | 3/5/18 8:00 AM | 3/16/18 5:00 PM | 15 | Project Manager
30 |  | contract resources | 10 days | 3/19/18 8:00 AM | 3/30/18 5:00 PM | 29 | Project Manager
31 | Confim Trading Partner cooperation |  | 15 days | 2/19/18 8:00 AM | 3/9/18 5:00 PM
32 |  | Leadership support | 5 days | 2/19/18 8:00 AM | 2/23/18 5:00 PM | 16
33 |  | Identify Project manager/key contacat | 5 days | 2/26/18 8:00 AM | 3/2/18 5:00 PM | 32 | Project Manager
34 |  | Direct care Staff | 5 days | 3/5/18 8:00 AM | 3/9/18 5:00 PM | 33 | Project Manager
35 |  | IT | 5 days | 3/5/18 8:00 AM | 3/9/18 5:00 PM | 33 | Project Manager
36 |  | Other | 5 days | 3/5/18 8:00 AM | 3/9/18 5:00 PM | 33 | Project Manager
37 | Identify sending and receiving vendor contacts |  | 5 days | 3/12/18 8:00 AM | 3/16/18 5:00 PM | 31 | Project Manager
38 | Hold Kick-off meeting |  | 5 days | 3/19/18 8:00 AM | 3/23/18 5:00 PM | 37 | Project Manager
39 | Confirm feasiblity of transaction with vendors |  | 25 days | 3/12/18 8:00 AM | 4/13/18 5:00 PM
40 |  | Confirm internal system capability | 5 days | 3/12/18 8:00 AM | 3/16/18 5:00 PM | 26 | IT,Vendor A | EHR system, HISP HIway Connection
41 |  | Confirm trading partner system capability | 5 days | 3/12/18 8:00 AM | 3/16/18 5:00 PM | 35 | Partner IT,Vendor A | EHR system, HISP HIway Connection
42 |  | Transaction data agreed | 10 days | 3/19/18 8:00 AM | 3/30/18 5:00 PM | 41 | IT,Partner IT,Care Staff Rep,Vendor B | Assuming structured data,
43 |  | Transport method agreed | 10 days | 3/19/18 8:00 AM | 3/30/18 5:00 PM | 41 | IT,Partner IT | Direct, VPN, SFTP other
44 |  | Ttransaction timing/frequency agreed | 10 days | 3/19/18 8:00 AM | 3/30/18 5:00 PM | 41 | Care Staff Rep,IT,Partner IT | How is the transaction triggered an how/when will it be sent? Batch, real-time
45 |  | Document Business and Clinical rules | 10 days | 3/19/18 8:00 AM | 3/30/18 5:00 PM | 41 | Project Manager,IT,Partner IT,Vendor A,Vendor B
46 |  | Document system changes required | 10 days | 3/19/18 8:00 AM | 3/30/18 5:00 PM | 41 | Project Manager
47 |  | contract for any required changes | 10 days | 4/2/18 8:00 AM | 4/13/18 5:00 PM | 46 | Project Manager | With vendor or contractor developing the interface
48 | IT systems |  | 10 days | 3/5/18 8:00 AM | 3/16/18 5:00 PM
49 |  | Ensure proper modules purchased, implemented and accessible | 5 days | 3/5/18 8:00 AM | 3/9/18 5:00 PM | 18 | IT | Each system must be able to send and receive
50 |  | Ensure User authentication, authorizations and other admin are complete | 5 days | 3/12/18 8:00 AM | 3/16/18 5:00 PM | 49 | IT | All appropriate users must be able to access information
51 | Legal Considerations |  | 30 days | 2/12/18 8:00 AM | 3/23/18 5:00 PM
52 |  | Consent | 30 days | 2/12/18 8:00 AM | 3/23/18 5:00 PM | 5 | Legal
53 |  | BAA | 30 days | 2/12/18 8:00 AM | 3/23/18 5:00 PM | 5 | Legal
54 |  | 42 CFR part 2 | 30 days | 2/12/18 8:00 AM | 3/23/18 5:00 PM | 5 | Legal
55 | Develop Implementation project plan |  | 5 days | 4/2/18 8:00 AM | 4/6/18 5:00 PM
56 |  | Document project requirements | 5 days | 4/2/18 8:00 AM | 4/6/18 5:00 PM | 46 | Project Manager
57 |  | Revise time estimate | 5 days | 4/2/18 8:00 AM | 4/6/18 5:00 PM | 46 | Project Manager
58 |  | Develop Contingency/Bail-out Plan | 5 days | 4/2/18 8:00 AM | 4/6/18 5:00 PM | 46 | Project Manager
59 | Revise Operational workflow |  | 30 days | 3/12/18 8:00 AM | 4/20/18 5:00 PM
60 |  | Evaluate current operational workflow | 10 days | 3/12/18 8:00 AM | 3/23/18 5:00 PM
61 |  | Sending organization workflow flowchart | 10 days | 3/12/18 8:00 AM | 3/23/18 5:00 PM | 25 | Project Manager,Care Staff Rep
62 |  | Receiving organization workflow flowchart | 10 days | 3/12/18 8:00 AM | 3/23/18 5:00 PM | 31 | Project Manager,Partner Care rep
63 |  | Document Future workflow | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM
64 |  | Document Sending organization Procedures | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM | 61 | Project Manager,Care Staff Rep | Include alternative, down-time, and/or emergency work-flows
65 |  | Document downtime/ Emergency workflow | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM |  | Project Manager,Care Staff Rep
66 |  | Hard copy documents and forms | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM | 61
67 |  | Fax Numbers and Contact Numbers | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM | 61
68 |  | Document Receiving organization Procedures | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM | 62 | Partner Care rep | Include alternative, down-time, and/or emergency work-flows
69 |  | Document downtime/ Emergency workflow | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM |  | Care Staff Rep,IT,Project Manager
70 |  | Hard copy documents and forms | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM | 61
71 |  | Fax Numbers and Contact Numbers | 10 days | 3/26/18 8:00 AM | 4/6/18 5:00 PM | 61
72 |  | Develop Work flow training plan | 10 days | 4/9/18 8:00 AM | 4/20/18 5:00 PM
73 |  | Trainers | 5 days | 4/9/18 8:00 AM | 4/13/18 5:00 PM | 64 | Care Staff Rep
74 |  | Materials | 5 days | 4/9/18 8:00 AM | 4/13/18 5:00 PM | 64 | Care Staff Rep
75 |  | Documentation | 10 days | 4/9/18 8:00 AM | 4/20/18 5:00 PM | 64 | Care Staff Rep
76 | Make interface coding changes |  | 16 days | 4/16/18 8:00 AM | 5/7/18 5:00 PM
77 |  | Code Changes | 10 days | 4/16/18 8:00 AM | 4/27/18 5:00 PM
78 |  | Sending system changes | 10 days | 4/16/18 8:00 AM | 4/27/18 5:00 PM | 47 | Vendor A,Vendor B
79 |  | Receiving system changes | 10 days | 4/16/18 8:00 AM | 4/27/18 5:00 PM | 47 | Vendor A,Vendor B
80 |  | Other (IE changes, ) | 10 days | 4/16/18 8:00 AM | 4/27/18 5:00 PM | 47 | Vendor A,Vendor B
81 |  | Complete coding | 0 days | 4/27/18 5:00 PM | 4/27/18 5:00 PM | 80 | Vendor A,Vendor B
82 |  | Perform all internal testing | 5 days | 4/30/18 8:00 AM | 5/4/18 5:00 PM | 77 | Vendor A,Vendor B
83 |  | Move code to test sytem | 1 day | 5/7/18 8:00 AM | 5/7/18 5:00 PM | 82 | Vendor A,Vendor B
84 | Testing |  | 29 days | 4/23/18 8:00 AM | 5/31/18 5:00 PM
85 |  | Document Testing Plan | 5 days | 4/23/18 8:00 AM | 4/27/18 5:00 PM
86 |  | document actors/scenario | 5 days | 4/23/18 8:00 AM | 4/27/18 5:00 PM | 72 | Project Manager,IT,Partner IT
87 |  | document data /scenario | 5 days | 4/23/18 8:00 AM | 4/27/18 5:00 PM | 72 | Project Manager,IT,Partner IT
88 |  | develop tests for all scenarios | 5 days | 4/23/18 8:00 AM | 4/27/18 5:00 PM | 72 | Project Manager,IT,Partner IT
89 |  | Confirm access to test system | 5 days | 4/30/18 8:00 AM | 5/4/18 5:00 PM | 85 | Partner IT
90 |  | Unit test | 18 days | 5/8/18 8:00 AM | 5/31/18 5:00 PM
91 |  | send test transaction | 5 days | 5/8/18 8:00 AM | 5/14/18 5:00 PM | 83,89 | IT,Partner IT
92 |  | confirm delivery | 1 day | 5/15/18 8:00 AM | 5/15/18 5:00 PM | 91 | Partner IT
93 |  | Process message | 1 day | 5/16/18 8:00 AM | 5/16/18 5:00 PM | 92 | Care Staff Rep,IT,Partner Care rep,Partner IT
94 |  | validate data | 1 day | 5/17/18 8:00 AM | 5/17/18 5:00 PM | 93 | Care Staff Rep,Partner Care rep
95 |  | Unit test complete | 10 days | 5/18/18 8:00 AM | 5/31/18 5:00 PM | 94 | IT,Partner IT,Team,Vendor A,Vendor B
96 | Go Live |  | 46 days | 4/9/18 8:00 AM | 6/11/18 5:00 PM
97 |  | Document Go Live Plan | 5 days | 4/9/18 8:00 AM | 4/13/18 5:00 PM | 63,45 | Project Manager
98 |  | Perform work flow training | 5 days | 6/1/18 8:00 AM | 6/7/18 5:00 PM | 95 | Care Staff Rep,Partner Care rep,Training Resource
99 |  | Move code to live | 1 day | 6/1/18 8:00 AM | 6/1/18 5:00 PM | 95 | Vendor A,Vendor B
100 |  | Production test | 5 days | 6/4/18 8:00 AM | 6/8/18 5:00 PM
101 |  | Paralell end-to-end testing with Real Patient data | 5 days | 6/4/18 8:00 AM | 6/8/18 5:00 PM | 99 | Care Staff Rep,IT,Partner Care rep,Partner IT
102 |  | Go Live | 1 day | 6/11/18 8:00 AM | 6/11/18 5:00 PM | 101 | Team
103 | Measure performance, support and debug |  | 30 days | 6/12/18 8:00 AM | 7/23/18 5:00 PM |  | Team
104 |  | Objective1 | 30 days | 6/12/18 8:00 AM | 7/23/18 5:00 PM | 102 | Team
105 |  | Objective 2 | 30 days | 6/12/18 8:00 AM | 7/23/18 5:00 PM | 102 | Team